## Sheet1
Lofthus Frukt og Saft Gantt Chart
| In Charge | Week Start | Estimate | Actual | % Complete | Week
Date Started 2 March 2020 | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Date of Finish 20 September 2020
PHASE 1: Information Gathering
Meeting & Setting Goals | ALL | 1 | 1 | 1 | 100% | bar: Week 1
Research & Targeting Audience | ALL | 1 | 1 | 1 | 100% | bar: Week 1
Review Existing Architecture | ALL | 2 | 2 | 2 | 100% | bar: Week 2 to Week 3
Phase 2: Planning
Site Map | PM,UD,WD,GD | 3 | 2 | 2 | 100% | bar: Week 3 to Week 4
Interaction Diagrams & Wireframes | PM,UD,WD,GD,C | 4 | 2 | 2 | 100% | bar: Week 4 to Week 5
Phase 3: Design
Contents, Images & Logo | PM,WD,C,GD,UD | 6 | 1 | 2 | 100% | bar: Week 6 to Week 7
Initial Design & Style Tiles | C,WD,GD,UD | 7 | 2 | 1 | 100% | bar: Week 7 to Week 8
Page Layouts | PM,WD,C,GD,UD | 8 | 2 | 2 | 50% | bar: Week 8 to Week 9
Clients Feedback | C,PM,WD | 10 | 1 |  | NS | bar: Week 10
Redesign & Refine | PM,WD,C,GD,UD | 11 | 2 |  | NS | bar: Week 11 to Week 12
Phase 4: Coding
Build Website | PM,WD,GD,UD | 13 | 8 |  | NS | bar: Week 13 to Week 20
Review & Clients Feedback | PM,C,WD | 20 | 1 |  | NS | bar: Week 20
Redesign & Refine | PM,WD,UD,GD,C | 21 | 4 |  | NS | bar: Week 21 to Week 24
Phase 5: Test & Launch
Test & Upload to server | WD,SA | 25 | 1 |  | NS | bar: Week 25
Meeting & Finalization | ALL | 25 | 2 |  | NS | bar: Week 25 to Week 26
Final Design, Test & Launch Website | ALL | 27 | 3 |  | NS | bar: Week 27 to Week 29
Team Members:
Project Manager PM
Web Developer WD
Quality Assurance Tester QT
Server Administrator SA
Graphic Designer GD
User Interface Designer UD
Client C
Not Started NS